## Sheet1
Knowledge Mining Product Backlog Sample
Task Name | Owner | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 0 |  | No | No | High | In Progress | 16 | No
Stand-up Azure Subscription & Resources | Architect | Yes | Yes | Medium | Complete | 16 | Yes
Document business requirements and define the business case (share with team in DevOps/Teams) | Architect
Design and decide on an architecture that will meet the customer's business needs | Architect
Document architectural limitations/constraints and set expectations with customer | Architect
Document project risks of varying severity levels and communicate the mitigation strategy | Architect
Conduct data assessment (availability, quantity, quality) and document findings | Data Scientist
Gather and document data model requirements and constraints | Data Scientist
Compile a report of the data assessment and model requirements and set data model expectations with customer | Data Scientist
Utilize Cognitive Search Accelerator IP to create and present a knowledge mining demo application to customer | Lead Developer
Define and document customer data architecture (storage and management) | Data Engineer
Conduct data cleansing and transformation on sample data for the demo application | Data Engineer
Integrate additional Cognitive Services into the demo application | Lead Developer | Yes | Yes | Medium | Complete | 0 | Yes
Sprint 1 (First) |  | Yes | Yes | Medium | In Progress | 96 | Yes
Stand-up Azure DevOps environment (define organization & project, start-up Azure Repos, Boards, and/or Pipelines) | Lead Developer | Yes | Yes | Low | Complete | 32 | Yes
Integrate DevOps Pipelines with Azure Resources | Lead Developer | Yes | Yes | Low | Complete | 48 | Yes
Invite team members to the Azure environment (DevOps & Subscription) and document how to get started | Lead Developer
Identify any technical skills gaps and onboard the necessary specialized resources (i.e. Oracle DW data engineer, NodeJS staff developer) | Architect
Refine architecture based on newly available information regarding customer's business needs | Architect
Update architectural limitations/constraints and set expectations with customer | Architect
Update project risks and communicate additional mitigation plans to team and customer | Architect
Create additional Azure Resources based on updated architecture | Architect
Define the data formatting requirements needed for custom modeling and communicate requirements to the data engineer | Data Scientist
Build first initial model (i.e. custom NLP or cognitive skill depending on use case) | Data Scientist
Create test cases for data model | Data Scientist
Create ETL pipeline connecting Oracle DW to Cosmos DB based on data formatting requirements | Data Engineer
Perform data wrangling on Cosmos DB document collection based on data formatting requirements | Data Engineer
Document ETL operations for team and customer reference | Data Engineer
Update product backlog to reflect newly available information and sprint 0 outcomes | Lead Developer
Define Cosmos DB document format based on web application requirements | Lead Developer
Sync with data team on Cosmos DB document format based on web application and data model requirements | Lead Developer
Integrate Application Insights into the source code for tracking and logging of activity | Lead Developer
Onboard new staff developer (AngularJS) and set expectations for the duration of the project | Lead Developer | No | No | Medium | Complete | 16 | No
Sprint 2 (Iterative) |  | Yes | No | Medium | In Progress | 32 | No
Identify any technical skills gaps and onboard the necessary specialized resources (i.e. Oracle DW data engineer, NodeJS staff developer) | Architect | Yes | No | Low | In Progress | 8 | No
Update product backlog to reflect newly available information and previous sprint outcomes | Lead Developer
Integrate Azure Active Directory into the web application | Lead Developer
Update web application requirements with new persona - contractor | Lead Developer | No | Yes | Medium | In Progress | 8 | No
Enable contractors to attach and upload files in the UI | Staff Developer
Build a PDF viewer (similar to customer's current website) into the UI | Staff Developer
Enable users to annotate and highlight documents in the UI | Staff Developer
Capture uploaded files fron the UI and stream them to Azure Storage | Lead Developer
Capture annotations and highlights and read them to Cosmos DB | Lead Developer
Create Role-based Access Management | Lead Developer
Migrate sample dataset from Oracle DW to Azure SQL DW instance | Data Engineer
Migrate raw files from multiple customer sources into Azure Storage (Blob) | Data Engineer
Define and build custom filters and tags to optimize search based on customer needs | Lead Developer
Perform data wrangling on Azure SQL DW data based on data formatting requirements | Data Scientist
Assess all correctly formatted data and perform feature engineering where appropriate | Data Scientist
Performane tune in initial model | Data Scientist
Report performance improvement of model to internal team | Data Scientist | Yes | No | Medium | In Progress | 16 | No
Sprint 3 (Iterative) |  | Yes | Yes | Medium | In Progress | 64 | Yes
Identify any technical skills gaps and onboard the necessary specialized resources (i.e. Oracle DW data engineer, NodeJS staff developer) | Architect | Yes | No | Low | Not Started | 32 | No
Update product backlog to reflect newly available information and previous sprint outcomes | Lead Developer | Yes | Yes | Low | Not Started | 32 | Yes
Review Cosmos DB data model and update to reflect any newly available information or previous sprint outcomes | Lead Developer
Create feature where web application recommends users other documents based on the one they are viewing | Lead Developer
Create feature where users can save specific search queries for later use | Staff Developer
Update Application Insights to refine tracking and logging of web application activity | Lead Developer
Update web application requirements with new persona - people manager | Lead Developer
Render document specifications as HTML in web browser | Staff Developer
Add browser support for Interent Explorer version 8 (customer standard browser) | Staff Developer
Create custom skill for Cognitive Search to detect dates in documents (written and numbered) | Lead Developer
Create custom skill for Cognitive Search to detect documents with substantial handwriting | Lead Developer
Surface custom skills to the web application as selectable filters | Staff Developer
Create feature that auto-generates summary cards for each document in search results | Lead Developer
Create a POC custom skill of the custom model being created by Data Scientist to visually present value of finalized model to customer | Lead Developer
Create a PBI Dashboard and connect it to Application Insights data | Data Engineer
Refine PBI dashboard based on client requirements (i.e. connect to Oracle DW for additional data) | Data Engineer
Performane tune in iterative model | Data Scientist
Report performance improvement of model to internal team | Data Scientist | Yes | Yes | Medium | Not Started | 0 | Yes
Sprint 4 (Final) |  | No | No | Low | Not Started | 64 | No
Develop a comprehensive test plan | Lead Developer | No | No | Low | Not Started | 48 | No
Perform end-to-end functional internal testing of the web application | Lead Developer | No | No | Low | Not Started | 8 | No
Perform UAT of web application | Lead Developer
Report testing results to team | Lead Developer
Presentation of web application and custom model results to client | Team | No | No | Low | Not Started | 8 | No

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started